MEMORA 
PROJECT EXECUTION PLAN

Context-Aware Cognitive AI Architecture

4-Person Team  |  12-Week Build-to-Paper Sprint

From Architecture Diagram → Publishable IEEE Paper

| T1 Identity & Biometrics | T2 Memory System | T3 Trust Engine | T4 LLM Pipeline & Eval |
| --- | --- | --- | --- |

OVERVIEW: HOW YOUR ARCHITECTURE MAPS TO THE PAPER

Your flowchart already IS the system. The execution plan below treats each major branch of the diagram as a buildable module and maps it to a research contribution, a code deliverable, and an experiment. The paper writes itself once the modules run.

LEFT BRANCH of diagram → Memory System (T2): query embedding, graph lookup, FAISS search, cross-encoder re-ranking, recency/emotion scoring, memory write-back RIGHT BRANCH of diagram → Identity & Biometrics (T1): camera capture, face recognition, speaker verification, pose weight calculation, identity table CENTRE-BOTTOM of diagram → Trust Engine (T3): trust score calculation, 3-tier access gate, temporal smoothing, identity confidence threshold FINAL OUTPUT path → LLM Pipeline & Eval (T4): context assembly, response generation, tone modulation, fallback/refusal, TTS output

The 3 Core Claims Your Paper Must Prove

- Claim A: Trust-conditioned retrieval (TCMRS scoring function) improves memory relevance precision over vanilla RAG and Generative Agents baseline.

- Claim B: Identity-resolution pre-authentication reduces unauthorised memory exposure vs. systems that assume authenticated users.

- Claim C: Emotion-weighted memory retrieval improves emotionally coherent response rate on EmpatheticDialogues benchmark.

TEAM ROLES & OWNERSHIP

Each member owns one module end-to-end: design, code, experiment, and paper section. This avoids integration bottlenecks and gives every person a clear authorship contribution.

Teammate 1 (T1) — Identity & Biometrics Lead

Owns: Camera pipeline → Face recognition → Speaker verification → Identity table • Implement ArcFace (InsightFace) face embedding pipeline from webcam frames • Implement ECAPA-TDNN speaker embedding from Whisper audio chunks • Build Identity Confidence IC(u,I) = weighted cosine fusion of face + voice • Maintain SQLite Identity Table: face_vector, voice_vector, last_seen, trust_seed • Write paper Section: Multimodal Identity Resolution (Section 3.1 of paper)

Teammate 2 (T2) — Memory System Lead

Owns: Memory stores → FAISS retrieval → Cross-encoder re-ranking → Scoring function • Build 4 memory tables: Episodic, Semantic, Emotional, Identity (SQLite + FAISS index) • Implement multi-factor retrieval score S(m,q,u) with alpha/beta/gamma/delta weights • Implement recency decay R(t) = exp(-lambda * delta_t) with 3 lambda ablations • Implement emotional saliency tag at memory write-time (valence + arousal threshold) • Integrate ms-marco-MiniLM cross-encoder for post-FAISS re-ranking • Write paper Section: Memory Architecture & Retrieval Scoring (Section 3.2)

Teammate 3 (T3) — Trust Engine Lead

Owns: Trust score computation → 3-tier access gate → Temporal smoothing → Privacy penalty • Implement T(u,t) dynamic trust update with decay, behavioral consistency, emotion signal • Implement 3-tier gate: High (>=0.80) / Medium (0.50-0.79) / Low (<0.50) • Implement privacy penalty P(m, T(u)) that blocks above-clearance memories in scoring • Implement trust reset trigger when IC drops below theta_known • Design annotation scheme for Trust Calibration Error (TCE) ground-truth labels • Write paper Section: Trust Engine & Access Control (Section 3.3)

Teammate 4 (T4) — LLM Pipeline & Evaluation Lead

Owns: Context assembly → LLM generation → Tone modulation → Evaluation harness • Build context assembler: trust tier + retrieved memories + emotion state → system prompt • Implement tone modulation templates per trust tier (High/Medium/Low response styles) • Implement refusal/fallback for Low-trust and failed-identity paths • Build full evaluation harness: Precision@K, Memory Faithfulness (RAGAs), TCE, Emotional Lift • Run all baselines: Vanilla RAG, Generative Agents memory, MemoryBank • Write paper Section: Experiments & Results (Section 4) + Related Work (Section 2)

12-WEEK SPRINT PLAN

Three phases, each 4 weeks. Phase 1 = Foundation (build). Phase 2 = Integration (connect). Phase 3 = Evaluation + Paper (prove and write).

PHASE 1 (Weeks 1–4) — BUILD MODULES IN PARALLEL

| Task / Deliverable | Owner | Sprint | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Whisper STT pipeline + audio chunking | T1 | Wk 1 | — | Audio → transcript + timestamps working |
| Face capture at 15fps, ArcFace embedding extraction | T1 | Wk 1 | — | 128-d face vector per frame, <50ms/frame |
| Speaker embedding (ECAPA-TDNN) from audio chunk | T1 | Wk 2 | T1-Wk1 audio | 192-d speaker vector per 2s chunk |
| IC(u,I) fusion function + identity table (SQLite) | T1 | Wk 3 | Face + voice vectors | Known vs unknown F1 > 0.90 on LFW subset |
| Identity threshold tuning (theta_new, theta_known) | T1 | Wk 4 | IC function | Precision-recall curve documented |
| FAISS index setup (4 memory partitions) | T2 | Wk 1 | — | Index create/insert/search in <10ms |
| Emotion tagger at memory write-time (valence+arousal) | T2 | Wk 2 | — | Emotion score [0,1] stored per memory chunk |
| Recency decay R(t) implementation + lambda sweep | T2 | Wk 2 | FAISS index | 3 lambda values benchmarked on MSC dataset |
| Multi-factor scoring S(m,q,u) — first version (fixed weights) | T2 | Wk 3 | Decay + emotion | Retrieval Precision@5 measured vs cosine baseline |
| Cross-encoder re-ranking (ms-marco-MiniLM) integration | T2 | Wk 4 | FAISS top-K | Precision@5 improvement quantified |
| Trust score T(u,t) update function | T3 | Wk 1 | — | Score updates correctly on scripted interaction log |
| 3-tier access gate (High / Medium / Low) logic | T3 | Wk 2 | Trust score | Gate blocks correct memories per tier in unit tests |
| Privacy penalty P(m, T(u)) in scoring function | T3 | Wk 3 | T3-Wk2 gate + T2 score | High-clearance memories blocked for Low-trust users |
| Trust reset on IC drop + temporal smoothing | T3 | Wk 4 | T1 IC function | Reset triggers correctly on simulated identity failure |
| LLM backbone setup (LLaMA-3-8B-Instruct local) | T4 | Wk 1 | — | Model serving at <2s/response on GPU |
| Context assembler: memory + trust + emotion → prompt | T4 | Wk 2 | T2 retrieval, T3 gate | Prompt correctly reflects trust tier in system message |
| Tone modulation templates (3 tiers) | T4 | Wk 3 | Context assembler | Human eval: tone correctly matches trust tier 80%+ |
| Refusal/fallback path for Low-trust + Unknown identity | T4 | Wk 4 | T3 gate, T1 IC | Correct refusal on 100% of scripted Low-trust inputs |

PHASE 2 (Weeks 5–8) — INTEGRATION + FIRST END-TO-END RUN

| Task / Deliverable | Owner | Sprint | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Integration: T1 identity output → T3 trust gate input | T1+T3 | Wk 5 | T1-Wk4, T3-Wk2 | IC score flows into trust tier selector correctly |
| Integration: T2 retrieval score uses T3 trust + T1 IC | T2+T3 | Wk 5 | T2-Wk3, T3-Wk3 | S(m,q,u) uses live trust score and privacy penalty |
| Integration: T4 context assembler receives T2 memories | T2+T4 | Wk 5 | T2-Wk4, T4-Wk2 | End-to-end: voice → memory → response working |
| First full pipeline smoke test on 5 scripted personas | ALL | Wk 6 | All Wk5 integrations | System produces correct-tier response for all 5 personas |
| Emotion detection module (SpeechBrain + facial affect) | T1 | Wk 6 | T1 audio/video pipeline | Valence+arousal score per utterance, used by T2+T3 |
| Learnable weight MLP for alpha/beta/gamma/delta (optional) | T2 | Wk 6 | S(m,q,u) baseline | MLP improves Precision@5 over fixed weights |
| Annotation tool: label 200 interactions with trust ground truth | T3 | Wk 6-7 | Scripted personas | 200 interactions labeled, inter-annotator kappa > 0.7 |
| Evaluation harness: Precision@K, RAGAs, TCE metrics | T4 | Wk 6-7 | Full pipeline running | All metrics compute without error on test set |
| Bug-fix sprint + latency profiling | ALL | Wk 8 | Wk 5-7 integrations | End-to-end latency <3s; no crash on 100 consecutive inputs |

PHASE 3 (Weeks 9–12) — EXPERIMENTS, ABLATIONS + PAPER WRITING

| Task / Deliverable | Owner | Sprint | Depends On | Done When |
| --- | --- | --- | --- | --- |
| Baseline 1: Vanilla RAG (Lewis et al.) — run on DailyDialog + MSC | T4 | Wk 9 | Eval harness | Precision@5 and Faithfulness Score recorded |
| Baseline 2: Generative Agents memory — run on same datasets | T4 | Wk 9 | Eval harness | Recency+importance scoring benchmarked |
| Baseline 3: MemoryBank — run on same datasets | T4 | Wk 9 | Eval harness | Ebbinghaus decay baseline recorded |
| Ablation A: System with trust=1.0 for all (no trust gate) | T3+T4 | Wk 9 | Full pipeline | Shows trust gate contribution to Precision@K |
| Ablation B: System with gamma=0 (no emotional weighting) | T2+T4 | Wk 9 | Full pipeline | Shows emotion contribution to Emotional Relevance Lift |
| Ablation C: System without identity resolution (assume auth) | T1+T4 | Wk 9 | Full pipeline | Shows IC gate contribution to unauthorised memory block rate |
| EmpatheticDialogues experiment: emotion-weighted retrieval | T2+T4 | Wk 10 | Ablation B done | Statistically significant lift in emotional coherence (p<0.05) |
| Human eval study: 3 annotators, 60 responses, appropriateness | ALL | Wk 10 | Full pipeline | Fleiss kappa > 0.65; appropriateness score by trust tier |
| Results table compilation + significance tests | T4 | Wk 10 | All experiments | All results in one LaTeX table; t-test p-values computed |
| Paper: Abstract + Introduction + Related Work | T4 | Wk 11 | Gap analysis doc | 2-page draft, reviewer-ready related work with 18 citations |
| Paper: System Architecture section (Sections 3.1–3.3) | T1+T2+T3 | Wk 11 | Each member's notes | All 5 equations in LaTeX; architecture figure from flowchart |
| Paper: Experiments section + Results tables | T4 | Wk 11 | Results table | Complete Section 4 with all ablation results |
| Internal review: each member reviews another's section | ALL | Wk 12 | All sections drafted | Review comments addressed; no undefined variables |
| Final paper polish + submission formatting (IEEE template) | ALL | Wk 12 | Internal review done | 8-page camera-ready in IEEE two-column format |

CRITICAL PATH & DEPENDENCIES

These are the integration points where one member blocks another. Resolve them first.

| Blocker | Blocks | Due By | Risk if Late |
| --- | --- | --- | --- |
| T1: IC(u,I) score output → defined JSON schema | T3 trust gate input; T4 context assembler | End of Week 3 | Trust engine cannot gate without identity confidence score |
| T2: S(m,q,u) scoring function interface defined | T3 privacy penalty plugs in; T4 context assembler calls it | End of Week 3 | Integration week (Wk 5) blocked if interface not stable |
| T3: Trust tier enum (HIGH/MED/LOW) → stable API | T4 tone modulation templates; T2 privacy penalty weight | End of Week 4 | T4 cannot build response templates without knowing tier format |
| T2+T3: Integration of trust score into scoring function | T4 evaluation harness (needs live S(m,q,u) values) | End of Week 5 | Evaluation in Phase 3 delayed; ablations cannot run |
| T3: 200 annotated interactions (TCE ground truth) | T4 can compute Trust Calibration Error metric | End of Week 7 | TCE metric missing from paper = weakens Claim A |
| T4: Evaluation harness fully operational | All Phase 3 experiments depend on it | End of Week 8 | Phase 3 compression — paper writing gets squeezed |

WEEKLY TEAM RITUALS (Non-Negotiable)

MONDAY (30 min) — Stand-up: each person states what they finished last week, what's blocked, and what they'll finish this week. Update the sprint table above. WEDNESDAY (1 hr) — Integration session: anyone whose output feeds another member's input merges and tests the handoff. This is where IC → Trust and Memory → LLM connect. FRIDAY (30 min) — Demo: whoever has a runnable component demos it to the group. Even partial demos. This catches wrong assumptions early. SHARED REPO — Single GitHub repo, one branch per member (T1/T2/T3/T4), merge to main only on Fridays after demo passes. Each member writes unit tests for their module.

PAPER SECTION ASSIGNMENTS

| Section | Owner | Content | Due |
| --- | --- | --- | --- |
| Abstract | T4 | 1 paragraph: problem, method, 3 key results, venue claim | Week 11 |
| 1. Introduction | T4 | Motivation, 3 claims, paper structure, figure of full system | Week 11 |
| 2. Related Work | T4 | 18 papers from literature review; explicit gap-to-section mapping | Week 11 |
| 3.1 Identity Resolution | T1 | IC equation, ArcFace + ECAPA-TDNN pipeline, threshold analysis | Week 11 |
| 3.2 Memory Architecture | T2 | 4 memory types, S(m,q,u) equation, FAISS + cross-encoder | Week 11 |
| 3.3 Trust Engine | T3 | T(u,t) equation, 3-tier gate, privacy penalty, reset logic | Week 11 |
| 3.4 Response Generation | T4 | Context assembly, tone templates, refusal mechanism | Week 11 |
| 4. Experiments | T4 | Baselines, 3 ablations, datasets, metrics, results tables | Week 11 |
| 5. Discussion | ALL | Limitations, future work, ethical considerations | Week 12 |
| 6. Conclusion | T4 | Restate claims, confirm results, venue contribution statement | Week 12 |

YOUR FIRST WEEK: EXACT NEXT STEPS

Stop planning. Start these today.

T1 — Do This Week

- pip install insightface onnxruntime speechbrain torch torchaudio whisper

- Write face_encoder.py: input=webcam frame (BGR), output=128-d numpy vector using ArcFace R50

- Write speaker_encoder.py: input=2s audio chunk (16kHz), output=192-d vector using ECAPA-TDNN

- Test on 3 different people, 5 samples each — confirm within-person cosine > 0.80, cross-person < 0.50

T2 — Do This Week

- pip install faiss-cpu sentence-transformers sqlalchemy

- Create memory_schema.sql: 4 tables (episodic, semantic, emotional, identity) with emotion_score + timestamp columns

- Write memory_store.py: insert_memory(text, type, emotion_score, timestamp) → embeds + stores in FAISS + SQLite

- Write memory_retrieve.py: query(text, top_k=20) → FAISS search → apply R(t) decay → return ranked list

T3 — Do This Week

- Write trust_engine.py: class TrustEngine with update(user_id, behavior_consistency, emotion_signal) → float

- Implement 3-tier classifier: score >= 0.80 → HIGH, 0.50-0.79 → MEDIUM, <0.50 → LOW

- Write 10 unit tests: verify trust updates correctly, tier boundaries correct, decay works over time

- Define the JSON contract that T1 will send to you: {user_id, IC_score, face_confidence, voice_confidence}

T4 — Do This Week

- Set up LLaMA-3-8B-Instruct via Ollama (ollama pull llama3) or Hugging Face transformers

- Write context_assembler.py: inputs=(retrieved_memories[], trust_tier, emotion_state) → formatted system prompt string

- Write 3 prompt templates (one per trust tier) — HIGH: full memory access + warm tone; MEDIUM: partial + neutral; LOW: restricted + formal

- Test full stub pipeline: hardcode a fake identity + trust + memory → verify LLM produces different responses per tier

END OF WEEK 1 CHECKPOINT (Friday demo): Each member runs their module on a 30-second scripted interaction clip (same clip for everyone). T1 outputs an IC score. T2 stores and retrieves 5 memories. T3 classifies a trust tier. T4 generates a response for that tier. No integration yet — just prove each piece works independently. Screenshot / log the output and share in the group chat.

—  Build first. Prove second. Write third.  —